## Sheet1
EKITI STATE CONTRACTORS' DEBT STATUS AS AT 31ST DECEMBER, 2021
S/N | Contractor | Contract Details | Executing MDAs | Date of Award | Contract Sum (A) | Variation (if any) (B) | Total Contract sum C (A+B) | Cummulative Certificate raised (D) | Cummulative Amount Paid (E) | Outstanding Balance on Work Done (D-E) | Remarks
1 | Dortmund Coy Ltd | Renovatn of Gen. Hosp. Ijan Ise & Emure | Special Project | 2013-07-19 | 147608610.15 |  | 147608610.15 | 104465910.35 | 73883398.07 | 30582512.28
2 | Amec Consuit Ltd | Renovatn of Gen. Hosp.Okemesi & Ijero | Special Project | 2013-07-19 | 120019713.39 |  | 120019713.39 | 114739006.59 | 86499655.5 | 28239351.09
3 | Mutual Dynamic Engr Ltd | Constr.of Training Hall at ADP office | Special Project | 2013-11-07 | 43918296 |  | 43918296 | 25489994.23 | 15575384.96 | 9914609.27
4 | Fatub Eng Ltd | Reno of General Hospitasl in Ayede,Oye & Ilupeju Ekiti | Special Project | 2013-07-19 | 136784607.7 |  | 136784607.7 | 74949907.34 | 42495701.83 | 32454205.51
5 | Support & Dev Ltd | Reno.of General Hospitals in Ifaki & Otun Ekiti | Special Project | 2013-07-19 | 68909135.95 |  | 68909135.95 | 57054322.26 | 21104692.44 | 35949629.82
6 | Nigerite Ltd | Construction of Ekiti Samsung ICT Center by Nigerite Ltd | Special Project |  | 42652615.72 | 11665062.62 | 54317678.34 | 51601794.42 | 31346817.49 | 20254976.93
7 | Sanju Sunny Nig | Irele-Ponyan Road | Works | 2013-02-04 | 848011338.5 | 50000000 | 898011338.5 | 849139211.13 | 662347717.79 | 186791493.34
8 | Anchor Maric Nig. Ltd. | Ado Township Road (Group C) | Works | 2012-07-19 | 643578559.32 |  | 643578559.32 | 613078837.65 | 420740234.2 | 192338603.45
9 | C.G.C Nig. Ltd. | Ijero-Ipoti-Iloro-Ayetoro | Works | 2012-03-28 | 956103986.26 |  | 956103986.26 | 910836648.57 | 846833829.75 | 64002818.82
10 | Charvet Nig. Ltd. | Oye-Ikun Road | Works | 2011-11-24 | 1002883612.5 | 255567890 | 1258451502.5 | 985248940.2 | 975684321.97 | 9600618.23
11 | Stateco Nig Ltd | Igede-Awo-Ido Road | Works | 2011-11-24 | 995662458 |  | 995662458 | 858736153.18 | 761819271.47 | 96916881.71
12 | Ratcon Constru Co.Ltd | Reha.of Aramoko-Ijero-Ido Rd | Works | 2011-08-26 | 1159412592.5 | 342590960.25 | 1502003552.75 | 1339687273.69 | 994864783.61 | 344822490.08
13 | Kitwood Nig Ltd | Pyt for the furnishing of New Govt Lodge | GH&P | 2014-08-18 | 604961645.72 |  | 604961645.72 | 574713563.43 | 562480822.85 | 12232740.58
14 | AFC World Nig Ltd | Additional furnishing of the D/Govr lodge | GH&P | 2018-02-20 | 11400100 |  | 11400100 | 10779511.8 | 10240536.2 | 538975.6
15 | Profit land West Africa Ltd | Pyt for the reno.of State Secretariat Creche | Women Affairs | 2012-03-09 | 4871002.5 |  | 4871002.5 | 4871002.5 | 2014077.99 | 2856924.51
16 | Construcciones Vera Nig.Ltd | Rehabilitation of Ado township Rd (Group B) | Works | 2012-07-30 | 582897538.13 |  | 582897538.13 | 518121870.15 | 412195051.66 | 6926818.49
17 | VYNOUAD CONST. COY | Construction of New Govr's Office, Ado Ekiti | works | 2016-09-28 | 1349364658.51 | 501567120.49 | 1850931779 | 1850839219.87 | 1849272099.38 | 1567120.49
18 | Matob-Gold Ventures Ltd | Re-Award of contract on the construction of New High Court Complex in Ado-Ekiti | Works | 2017-08-21 | 613333574.04 |  | 613333574.04 | 602666896.02 | 506666787.02 | 96000109
19 | August Ten Concept Global Resource Ltd | Constrution of Gate House to Governor's Office. | works | 2017-02-15 | 2782771.72 |  | 2782771.72 | 2782771.72 | 1536404.93 | 1246366.79
20 | Pleasant Design Concept Ltd | Construction Veterinary Clinic, Ado Ekiti. | works | 2015-10-22 | 24254767.37 |  | 24254767.37 | 24254767.37 | 22067033.21 | 2187734.16
21 | Team Electric Ltd | Installation of double Arm led street lights for Imugbagba-Odoado dual carriage rd, Ado-Ekiti. | Works | 2016-12-13 | 14762355.3 |  | 14762355.3 | 14762355.3 | 13424237.54 | 1338117.76
22 | Skill 'G' Nig Ltd | Upgrading of Equipment & Facilities at Govt Technical College, Ado-Ekiti | BTVE | 2018-05-03 | 1875107208.02 |  | 2047822330.98 | 1781351847.62 | 1772800889.38 | 8550958.24
23 | Mega Modules Nig. Ltd | Additional works/ Variation on the construction of Gifted Int'l Academy, Afao-Ekiti | SUBEB | 2018-09-17 | 21286090.11 |  | 21286090.11 | 21286090.11 | 20079285.6 | 1206804.51
24 | Hartland Nig. Ltd. | Dualization of First Baptist Atikankan Rd | Works | 24/11/11 | 891822525.3 | 192638776.46 | 1084461301.76 | 1027920975.37 | 927369105.35 | 100551870.02
25 | kopek Const. Ltd. | Dualization of Omuo Ekiti Township Road | Works | 16/2/16 | 192157646.63 | 0 | 192157646.63 | 169694774.01 | 164650635.53 | 5044138.48
26 | Genius Jack Engineering Coy Ltd | Rehabilitation of Ado-Afao Road | Works | 23/2/18 | 213784956 | 0 | 213784956 | 106892478 | 100000000 | 6892478
27 | Hartland Nig. Ltd. | Dualization of Old-Garage Ojumose Road | works | 24/11/11 | 1032438301.1 | 0 | 1032438301.1 | 945474201.27 | 939077458.1 | 6396743.17
28 | KOPEK CONST. LTD | Constr. Of Awedele Road, Ado-Ekiti. | Works | 30/7/15 | 156080465.63 | 332119508.96 | 488199974.59 | 483941612.99 | 483126363.67 | 815249.32
29 | Adetoun Nig. Ltd | Land Clearing of 25 hectares | Agric | 20/6/19 | 8842866.75 |  | 8842866.75 | 4421433.38 | 0 | 421433.38
30 | FAKTOPS Global Concepts Ltd | Procurement of Science Laboratory Equipment to all Secondary Schools in Ekiti State (5 & 16) | Education, Science & Technology | 13/6/19 | 10605000 |  | 10605000 | 12605000 | 7802500 | 802500
31 | Lanny Gooddeal Multrinational Concept Ltd | Procurement of Science Laboratory Equipment to all Public secondary schools in Ekiti State LOT 13 | Education, Science & Technology | 19/6/19 | 5151000 |  | 5151000 | 5151000 | 5000000 | 151000
32 | Lanny Gooddeal Multrinational Concept Ltd | Procurement of Science Laboratory Equipment to all Public secondary schools in Ekiti State LOT 15 | Education, Science & Technology | 19/6/19 | 14140000 |  | 14140000 | 14140000 | 9970000 | 570000
| TOTAL (A) | [8 empty] | 1308166273.03
RETENTION ( B )
33 | J.K Furniture Nig Ltd | furnishing of VIP Chalets at the Govt House | GH&P | 2011-07-23 | 8309700 |  | 8309700 | 8309700 | 7894215 | 415485
34 | Special Hold Dev Coy Ltd | Constr.of 8 blocks of open mkt stalls & d demolished Odua Textile fence,Awedele Ado | Urban Renewal | 2013-12-08 | 29855760.8 |  | 29855760.8 | 29855760.8 | 28536924.78 | 1318836.02
35 | Tutu Global Ventures | Construction of Security Gate at Samsung Engineering Academy Govt Technical College, Ado-Ekiti | BTVE | 2017-11-14 | 1990150 |  | 1990150 | 1990150 | 1890642.5 | 99507.5
36 | Canaan Towers Ltd | Additional work on the renovation of a block of Science Laboratory at Osi Community High Schl, Osi-Ekiti | Education | 2017-05-27 | 3559975 |  | 3559975 | 3559975 | 3381976.25 | 177998.75
37 | Canaan Towers Ltd | Renovation of Laboratory Block at Osi Community High Schl, Osi-Ekiti | Education | 2018-07-02 | 5010348.74 |  | 5010348.74 | 5010348.74 | 4759831.3 | 250517.44
38 | Banta Enterprise Ltd | Installation of Street Light on Dualized State Roads. | Works | 2017-07-29 | 353893771.22 |  | 353893771.22 | 352153771.32 | 336199082.66 | 15954688.66
| TOTAL (B) | [8 empty] | 18217033.37
39 | Ideal Fundamental Consult. | Consultancy service on Oba Adejugbe Gen.Hosptal | Special Project |  | 32354405.91 |  | 32354405.91 |  | 15000000 | 17354405.91
40 | Enpro Consulting | Mgt. Consultancy on Road | Works | 28/3/12 | 174217500 |  | 174217500 |  | 149827050 | 24390450
41 | Casa Consuit Ltd | Consultancy service on ultra modern civil centre,Ado-Ekiti | Infrastructure | 2012-11-06 | 137611325.07 |  | 137611325.07 |  | 122130051 | 15481274.07
42 | Archi-Project Consortium | Consultancy fee on the construction of secretariat building phase v (Lot I-IV) | Infrastructure |  | 41044596.68 |  | 41044596.68 |  | 22939607.19 | 18104989.49
43 | Grids Associates Ltd | Consultancy fee on the construction of New High Court Complex, Ado-Ekiti Stage (1,2&3) | works | 29/7/16 | 103144138.98 |  | 103144138.98 |  | 99610236.18 | 3533902.8
44 | AD Consulting Ltd | Consultancy service on construction of Ekiti State Liaison office, Ikeja, Lagos State | Works | 2019-05-03 | 8839850.76 |  | 8839850.76 |  | 6635954.09 | 2203896.67
45 | Messrs AD Consulting Limited | Consultancy Services of Architectural Design of Ekiti Knowledge Zone | Investment Trade & industries | 2019-05-09 | 447511365 |  | 447511365 |  | 452654253.3 | 8380853.8
| TOTAL (C) | [8 empty] | 89449772.74
| TOTAL (A + B + C) | [8 empty] | 1415833079.14